## HRIS
SN | Type | Description | Date Opened | Date Closed | Status | Action By | Remarks
1 | User Error | Casuntingan - error in installing since it was installed as Corp instead of branch. | 2015-06-27 |  | Fixed | Nilo | [19-Sep] Feedback - Services from employees were overwritten; working as designed since it is supposed to do a 'clean' install of the system. Nilo to discuss with Exel. [8-Aug] Fixed [1-Aug] Corky to create installer to fix [27-Jun] Nilo to send the copy of Excel file. HR to hold upload of branch employees until this issue has been fixed
2 | Info | MIEF - Employee Number. Requirements provided is based on HRIS system generated series. To discuss link to payroll system so that one number will be used for both systems. | 2015-07-04 |  | On Hold | Nilo | [1-Aug] put on hold for now; currently still linking payroll to biometrics system. Nilo to discuss with Payroll and HR.
3 | Bug | MIEF - Date of Birth - shown in the system is 07/03/205, but inputted into the system is 07/30/1994 | 2015-07-04 | 2015-09-19 | Closed | Nilo | [19-Sep] Closed, verified [8-Aug] Fixed [1-Aug] Fix to be provided by 10-Aug. Format should be mm/dd/yyyy
4 | Info | MIEF - Effectivity Date - where does the system get this? Can this be inputted by HR personnel (there is sometimes a need to adjust entry date) Effective Date = Hired Date | 2015-07-04 | 2015-09-19 | Closed | Nilo | [19-Sep] Closed, verified [8-Aug] Fixed [1-Aug] Employee profile Start Date information to be populated into MIEF Effectivity Date field; show in print out
5 | CR | MIEF - Store Operations Manager - need a module where HR can input name of manager. This should be controlled by the Corp HR office - 'Approved by' - one time setup per branch, free text field, editable by Corp only - In Employee profile, add field to input 'Department Head'. This will be the data source for MIEF 'Noted by' section - Free text for 'Department Head' editable by Branch | 2015-07-04 |  | Open | Corky | [19-Sep] Requirements confirmed; for implementation [10-Aug] for Impact assessment [1-Aug] agreed with Nilo to defer CR since this is not a critical requirement [31-Jul] This needs a new screen in Corp for inputs, new table in db, store and synch logic from Corp to Branch. Can this be grouped with other CRs for a new release?
6 | Info | Acceptance form/template for HR to sign-off (Phase 1) | 2015-07-04 | 2015-09-19 | Closed | Nilo | [19-Sep] Closed for original scope Phase 1 [9-Aug] sign off form sent via email [1-Aug] acknowledgement form. K to create first page for sign-off and last page for requests. Nilo to attach forms
7 | CR | Error Message for Dashboard |  | 2015-06-27 | Closed | None
8 | CR | Grouping for more button |  | 2015-06-27 | Closed | None
9 | CR | Expiration is 1 year instead of 6 months |  | 2015-06-27 | Closed | None
10 | CR | When contract expires or upon resignation, can we add this status into the system? • Expire – in system • Terminated – need to add status • Resigned – need to add status Per employee, add Terminated and Resigned as part of the employee status drop down list. Terminated status can only be set by Corp. | 2015-06-27 |  | Open | Corky | [19-Sep] Requirements confirmed; for implementation [8-Aug] Estimate: 5 days [1-Aug] impact assessment to be done on CR; to advise by 10-Aug
11 | CR | Infractions – although this forms part of operations, there is a change in wordings | 2015-06-27 | 2015-09-19 | Closed | Nilo | [19-Sep] Closed, verified [8-Aug] Fixed [1-Aug] CK to amend [4-Jul] Code of Discipline sent (wordings changed only); CK to amend [27-Jun] Nilo to send template
12 | CR | New Positions – allow for free text entry for Corp, function cannot be done by branch. Only the lowest level can be free text – higher level (department) has to be defined, ie, Special Function >> Free text 'Special Function' is hard-coded, only the position following that will be free text | 2015-06-27 |  | Open | Corky | [19-Sep] Requirements confirmed; for implementation [8-Aug] Estimate: 10 days [1-Aug] CK to do impact assessment for next release
13 | Info | User manual update for final acceptance | 2015-08-01 | 2015-09-19 | Closed | Nilo | [19-Sep] Closed, verified [9-Aug] v0.2 sent via email [1-Aug] K to send updated user manual
14 | Info | For new releases, new installer will serve as a patch to existing installed systems. | 2015-08-01 |  | Closed | None
15 | CR | Infractions - add screen to manage Infractions. - Only Corp Admin can access this module - Add new infraction module, up to 10 levels of the infraction can be defined - Edit infraction module - Corp Admin can edit title and description for existing infractions but cannot add new levels - Synch to branches will be done by Force Synch - Ensure format that is ported into Word document will not be changed; restrict inputs to maximum characters to keep Word formatting intact | 2015-08-01 |  | Open | Corky | [19-Sep] Requirements confirmed; for implementation [8-Aug] Estimate: 7 days [1-Aug] CK to do impact assessment for next release
16 | Info | Acceptance form/template for HR to sign-off (Phase 2) | 2015-09-19 |  | Open | Kristine | [19-Sep] on hold until Phase 2 is completed
17 | Bug | Error Message for HRIS Dashboard and other errors | 2015-09-19 |  | Open | Nilo | [19-Sep] Nilo to send details
18 | Info | Phase 2 Schedule - Oct (UAT), Dec (Production roll-out) | 2015-09-19 |  | Open | Kristine | [19-Sep] FYI
19 |  | HRIS concerns as of 10-Oct'15 (refer to email with screenshots) | 2015-10-10 |  | Open | Corky
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35

## Dashboard
SN | Type | Description | Date Opened | Date Closed | Status | Action By | Remarks
1 | Info | Implementation and internal testing in progress | 2015-06-27 |  | Open | Nilo | [4-Dec] Expected to be ready by Jan'16 [19-Sep] Data mirror to be ready by 15-Oct [10-Aug] Next step is for testing with data mirror; pending updates on status by Sep [1-Aug] CK to update status
2 | Info | UAT to be done in 2 stages i. Data mirror – ~Nov ii. Actual Data Warehouse – Nov~Dec | 2015-06-27 |  | Open | CK, Nilo | [19-Sep] On hold until HW and DB is setup at GCSG
3 | Info | Data mirror - readiness date and connection details | 2015-06-27 |  | Open | Nilo | [19-Sep] Data mirror to be ready by 15-Oct [10-Aug] Estimate to be ready by Sep [1-Aug] Physical servers are with GSCG; schedule to be confirmed
4 | Info | Actual data warehouse - readiness date and connection details | 2015-06-27 |  | Open | Nilo | [1-Aug] schedule to be confirmed
5 | Info | Create baseline vs actual project plan - send to Nilo | 2015-08-10 |  | Closed | Kristine | [19-Sep] Sent on 19-Sep
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35

## HRIS UseCase
Use Case #
5.1 | Corp HR can set the 'Approved by'
5.2 | Sync 'Approved by' to specific branch
5.3 | MIEF printing uses 'Approved by' and Department Head as 'Noted by'
5.4 | HR can update employee's Department Head

## HRIS Seq Diagram
5.2.1 | Sync CORP to BRANCH ( approver for branch )
| CORP | BRANCH x
1 | CORP:HR user -> CORP:agm_branch | Update branch approver
2 | CORP:agm_branch -> CORP:agm_amsg_queue | publish_to_branch(branch_id, {branch_approver})
-- BRx:agm_sync scheduler
3 | BRx:agm_sync -> CORP:agm_sync | get_updates_from_corp(branch_id)
4 | CORP:agm_sync -> CORP:agm_amsg_queue | get_msg_for_branch(branch_id)
5 | CORP:agm_amsg_queue -> CORP:agm_sync | return { 'branch_approver', {branch_approver}}
6 | CORP:agm_sync -> BRx:agm_sync | return { 'branch_approver', {branch_approver}}
7 | BRx:agm_sync->BRx:agm_sync | sync_branch_approver( {branch_approver} )

## HRIS DB
5.1 | entity_agm_branch_approver
branch_id
approver
uuid
create_datetime
update_datetime